## Sheet2
| 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01
Completion of cis-eQTL analyses in the HIRD cohort | bar: 2018-04-01 to 2018-06-01
Comparison of identified eQTLs to known hits | bar: 2018-06-01 to 2018-08-01
Building predictive models for HIRD | bar: 2018-08-01 to 2018-11-01
Recruitment of Vacxin batch 1 samples | bar: 2018-06-01 to 2018-08-01
Processing and sequencing samples from Vacxin batch 1 | bar: 2018-09-01 to 2018-11-01
Recruitment of Vacxin batch 2 samples etc. | bar: 2018-09-01 to 2018-11-01
Adapting HIRD pipeline for analysis of Vacxin samples | bar: 2018-11-01 to 2019-01-01
Processing and sequencing samples from Vacxin batch 2 etc. | bar: 2018-12-01 to 2019-02-01
Incorporating new Vacxin samples into pipeline etc. | bar: 2019-02-01 to 2019-03-01

## Sheet1
Task | Start | Duration | End
Completion of cis-eQTL analyses in the HIRD cohort | 2018-04-01 | 61 | 2018-06-01
Comparison of identified eQTLs to known hits | 2018-06-01 | 61 | 2018-08-01
Building predictive models for HIRD | 2018-07-01 | 92 | 2018-10-01
Recruitment of Vacxin batch 1 samples | 2018-06-01 | 92 | 2018-09-01
Processing and sequencing samples from Vacxin batch 1 | 2018-09-01 | 91 | 2018-12-01
Adapting HIRD pipeline for analysis of Vacxin samples | 2018-11-01 | 92 | 2019-02-01
Recruitment of Vacxin batch 2 samples etc. | 2018-09-01 | 91 | 2018-12-01
https://www.smartsheet.com/blog/gantt-chart-excel